## Scenario_Input
Parameter | Value | Source | Type
Issue Type | Quality Issue - Firmware Defect on PCBA | Case study | Given
Affected SKU | A | Case study | Given
Affected Component | RM04 (PCBA) | BOM & Inventory | Given
BOM Usage (PCBA per FG) | 2 | BOM & Inventory R8 | Data
Issue Start Date | 2026-04-15 | Case study | Given
--- PCBA Inventory Status ---
On-hold stock at plant | 340000 | BOM & Inventory R8 | Data
On-hold pending PO at supplier | 30000 | BOM & Inventory R8 | Data
Total on-hold PCBA | 370000 | Calculated | Derived
PCBA unit price (USD) | 15 | BOM & Inventory R8 | Data
Total on-hold value (USD) | 5550000 | Calculated | Derived
--- Reflash Option ---
Reflash equipment arrival | 2026-05-06 | Case study (3 weeks) | Given
Reflash wait (calendar days) | 21 | Case study | Given
Reflash capacity per day | Unlimited (all stock) | Assumption | Assumption
Reflash yield | 100% | Assumption | Assumption
Reflash cost per unit (USD) | 0 | Assumption (equipment cost only) | Assumption
QC/release delay after reflash | 0 days | Assumption | Assumption
--- New Supply Option ---
Supplier new-build capacity | 4,000 PCBA/day | Case study | Given
Air lead time (calendar days) | 3 | Case study | Given
Sea lead time (calendar days) | 21 | Case study | Given
Air extra cost per PCBA (USD) | 2 | Case study | Given
Sea extra cost per PCBA (USD) | 0 | Baseline (no extra) | Assumption
--- Planning Horizon ---
Horizon start | 2026-04-15 | Case study | Given
Horizon end | 2026-05-15 | Case study | Given
Workdays in horizon | 27 | Calculated (Mon-Sat) | Derived
--- Recovery Decision ---
Recovery level chosen | 60% | recovery_analysis.py | Decision
Max A shortage allowed | 11674 |  | Derived
Air PCBA shipped | 35020 | Solver output | Output
Air freight cost (USD) | 70040 |  | Output

## PCBA_Recovery_Plan
Workday # | Date | Cal Day | Day Type | Opening On-Hold | Reflash Status | Reflash Avail Today | Cumul Reflashed | New Build at Supplier | Air Shipped | Sea Shipped | Air Arrived Today | Sea Arrived Today | Cumul New Usable | Total Usable PCBA | A Prod Today | PCBA Required Today | Cumul PCBA Consumed | Ending Usable Balance | PCBA Status
1 | 2026-04-15 | 0 | Workday | 370000 | WAITING (21 days left) | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BLOCKED
2 | 2026-04-16 | 1 | Workday | 370000 | WAITING (20 days left) | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BLOCKED
3 | 2026-04-17 | 2 | Workday | 370000 | WAITING (19 days left) | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BLOCKED
4 | 2026-04-18 | 3 | Workday | 370000 | WAITING (18 days left) | 0 | 0 | 4000 | 4000 | 0 | 4000 | 0 | 4000 | 4000 | 0 | 0 | 0 | 4000 | OK
5 | 2026-04-20 | 5 | Workday | 370000 | WAITING (16 days left) | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000 | 4000 | 510 | 1020 | 1020 | 2980 | OK
6 | 2026-04-21 | 6 | Workday | 370000 | WAITING (15 days left) | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 1020 | 2980 | OK
7 | 2026-04-22 | 7 | Workday | 370000 | WAITING (14 days left) | 0 | 0 | 4000 | 2020 | 0 | 2020 | 0 | 6020 | 6020 | 2500 | 5000 | 6020 | 0 | TIGHT
8 | 2026-04-23 | 8 | Workday | 370000 | WAITING (13 days left) | 0 | 0 | 4000 | 4000 | 0 | 4000 | 0 | 10020 | 10020 | 0 | 0 | 6020 | 4000 | OK
9 | 2026-04-24 | 9 | Workday | 370000 | WAITING (12 days left) | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 10020 | 10020 | 0 | 0 | 6020 | 4000 | OK
10 | 2026-04-25 | 10 | Workday | 370000 | WAITING (11 days left) | 0 | 0 | 4000 | 4000 | 0 | 4000 | 0 | 14020 | 14020 | 2500 | 5000 | 11020 | 3000 | OK
11 | 2026-04-27 | 12 | Workday | 370000 | WAITING (9 days left) | 0 | 0 | 4000 | 3000 | 0 | 3000 | 0 | 17020 | 17020 | 2500 | 5000 | 16020 | 1000 | OK
12 | 2026-04-28 | 13 | Workday | 370000 | WAITING (8 days left) | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 17020 | 17020 | 0 | 0 | 16020 | 1000 | OK
13 | 2026-04-29 | 14 | Workday | 370000 | WAITING (7 days left) | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 17020 | 17020 | 0 | 0 | 16020 | 1000 | OK
14 | 2026-04-30 | 15 | Workday | 370000 | WAITING (6 days left) | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 17020 | 17020 | 0 | 0 | 16020 | 1000 | OK
15 | 2026-05-01 | 16 | Workday | 370000 | WAITING (5 days left) | 0 | 0 | 4000 | 4000 | 0 | 4000 | 0 | 21020 | 21020 | 2500 | 5000 | 21020 | 0 | TIGHT
16 | 2026-05-02 | 17 | Workday | 370000 | WAITING (4 days left) | 0 | 0 | 4000 | 4000 | 0 | 4000 | 0 | 25020 | 25020 | 2000 | 4000 | 25020 | 0 | TIGHT
17 | 2026-05-04 | 19 | Workday | 370000 | WAITING (2 days left) | 0 | 0 | 4000 | 4000 | 0 | 4000 | 0 | 31020 | 31020 | 2500 | 5000 | 30020 | 1000 | OK
18 | 2026-05-05 | 20 | Workday | 370000 | WAITING (1 days left) | 0 | 0 | 4000 | 4000 | 0 | 4000 | 0 | 35020 | 35020 | 2500 | 5000 | 35020 | 0 | TIGHT
19 | 2026-05-06 | 21 | Workday | 0 | AVAILABLE | 370000 | 370000 | 4000 | 0 | 0 | 0 | 0 | 35020 | 405020 | 2500 | 5000 | 40020 | 365000 | OK
20 | 2026-05-07 | 22 | Workday | 0 | AVAILABLE | 0 | 370000 | 4000 | 0 | 0 | 0 | 0 | 35020 | 405020 | 2500 | 5000 | 45020 | 360000 | OK
21 | 2026-05-08 | 23 | Workday | 0 | AVAILABLE | 0 | 370000 | 4000 | 0 | 0 | 0 | 0 | 35020 | 405020 | 2500 | 5000 | 50020 | 355000 | OK
22 | 2026-05-09 | 24 | Workday | 0 | AVAILABLE | 0 | 370000 | 4000 | 0 | 0 | 0 | 0 | 35020 | 405020 | 2500 | 5000 | 55020 | 350000 | OK
23 | 2026-05-11 | 26 | Workday | 0 | AVAILABLE | 0 | 370000 | 4000 | 0 | 0 | 0 | 0 | 35020 | 405020 | 2500 | 5000 | 60020 | 345000 | OK
24 | 2026-05-12 | 27 | Workday | 0 | AVAILABLE | 0 | 370000 | 4000 | 0 | 0 | 0 | 0 | 35020 | 405020 | 2500 | 5000 | 65020 | 340000 | OK
25 | 2026-05-13 | 28 | Workday | 0 | AVAILABLE | 0 | 370000 | 4000 | 0 | 0 | 0 | 0 | 35020 | 405020 | 2500 | 5000 | 70020 | 335000 | OK
26 | 2026-05-14 | 29 | Workday | 0 | AVAILABLE | 0 | 370000 | 4000 | 0 | 0 | 0 | 0 | 35020 | 405020 | 2500 | 5000 | 75020 | 330000 | OK
27 | 2026-05-15 | 30 | Workday | 0 | AVAILABLE | 0 | 370000 | 4000 | 0 | 0 | 0 | 0 | 35020 | 405020 | 2500 | 5000 | 80020 | 325000 | OK

## Scenario_PP
SKU | Description | Market | Product Group | Fixture | Priority | Weekly Cap | Ship Request | Demand Qty | 15/04 | 16/04 | 17/04 | 18/04 | 20/04 | 21/04 | 22/04 | 23/04 | 24/04 | 25/04 | 27/04 | 28/04 | 29/04 | 30/04 | 01/05 | 02/05 | 04/05 | 05/05 | 06/05 | 07/05 | 08/05 | 09/05 | 11/05 | 12/05 | 13/05 | 14/05 | 15/05 | Beg Inv | Period Prod | Available | PCBA Required | PCBA Allocated | End Inv | Shortage | Late Qty | Recovery Mode | Service Risk
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 2 | 3000 | 2026-05-01 | 588 | 500 | 500 | 500 | 500 | 500 | 500 | 0 | 500 | 500 | 500 | 500 | 500 | 30 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6030 | 6030 | 0 | 0 | 5442 | 0 | 0 | N/A | LOW
A | 2026 Automatic Robot ver | US | Electronic Toy | 123AB | 1 | 15000 | 2026-05-08 | 684 | 0 | 0 | 0 | 0 | 510 | 0 | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0 | 0 | 2500 | 2000 | 2500 | 2500 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25010 | 25010 | 50020 | 50020 | 24326 | 0 | 0 | Reflash | LOW
E | 2026 Scooter ver | Australia | Outdoor & Sports Toy | 789EF | 1 | 3000 | 2026-05-08 | 472 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 470 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1470 | 1470 | 0 | 0 | 998 | 0 | 0 | N/A | LOW
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 2 | 3000 | 2026-05-08 | 4028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 500 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 5442 | 3000 | 8442 | 0 | 0 | 4414 | 0 | 0 | N/A | LOW
A | 2026 Automatic Robot ver | US | Electronic Toy | 123AB | 1 | 15000 | 2026-05-15 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 24326 | 15000 | 39326 | 30000 | 30000 | 19326 | 0 | 0 | Reflash | LOW
B | 2025 Barbie ver colorful | US | Doll | 123AB | 2 | 15000 | 2026-05-15 | 5502 | 2500 | 2500 | 2500 | 2500 | 1990 | 2500 | 0 | 2500 | 2500 | 0 | 0 | 2500 | 2500 | 2500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27490 | 27490 | 0 | 0 | 21988 | 0 | 0 | N/A | LOW
C | 2026 Castle & Farm Blocks | UK | Building & Construction Toy | 456CD | 1 | 5000 | 2026-05-15 | 4320 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 0 | 22491 | 22491 | 0 | 0 | 18171 | 0 | 0 | N/A | LOW
D | 2026 Animal Animation Book | UK | Educational Toy | 456CD | 2 | 5000 | 2026-05-15 | 2430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2430 | 2430 | N/A | MEDIUM
E | 2026 Scooter ver | Australia | Outdoor & Sports Toy | 789EF | 1 | 3000 | 2026-05-15 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 998 | 0 | 998 | 0 | 0 | 698 | 0 | 0 | N/A | LOW
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 2 | 3000 | 2026-05-15 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 500 | 500 | 500 | 500 | 4414 | 3000 | 7414 | 0 | 0 | 3214 | 0 | 0 | N/A | LOW
A | 2026 Automatic Robot ver | US | Electronic Toy | 123AB | 1 | 15000 | 2026-05-22 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19326 | 0 | 19326 | 0 | 0 | 0 | 674 | 674 | Partial (60%) | HIGH
B | 2025 Barbie ver colorful | US | Doll | 123AB | 2 | 15000 | 2026-05-22 | 15658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21988 | 0 | 21988 | 0 | 0 | 6330 | 0 | 0 | N/A | LOW
C | 2026 Castle & Farm Blocks | UK | Building & Construction Toy | 456CD | 1 | 5000 | 2026-05-22 | 8370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18171 | 0 | 18171 | 0 | 0 | 9801 | 0 | 0 | N/A | LOW
D | 2026 Animal Animation Book | UK | Educational Toy | 456CD | 2 | 5000 | 2026-05-22 | 9990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9990 | 9990 | N/A | MEDIUM
E | 2026 Scooter ver | Australia | Outdoor & Sports Toy | 789EF | 1 | 3000 | 2026-05-22 | 698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 698 | 0 | 698 | 0 | 0 | 0 | 0 | 0 | N/A | LOW
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 2 | 3000 | 2026-05-22 | 3802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3214 | 0 | 3214 | 0 | 0 | 0 | 588 | 588 | N/A | MEDIUM
A | 2026 Automatic Robot ver | US | Electronic Toy | 123AB | 1 | 15000 | 2026-05-29 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 | 11000 | Partial (60%) | HIGH
B | 2025 Barbie ver colorful | US | Doll | 123AB | 2 | 15000 | 2026-05-29 | 8865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6330 | 0 | 6330 | 0 | 0 | 0 | 2535 | 2535 | N/A | MEDIUM
C | 2026 Castle & Farm Blocks | UK | Building & Construction Toy | 456CD | 1 | 5000 | 2026-05-29 | 11782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9801 | 0 | 9801 | 0 | 0 | 0 | 1981 | 1981 | N/A | HIGH
D | 2026 Animal Animation Book | UK | Educational Toy | 456CD | 2 | 5000 | 2026-05-29 | 5840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5840 | 5840 | N/A | MEDIUM
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 2 | 3000 | 2026-05-29 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 4500 | N/A | MEDIUM

## Scenario_Cost_Analysis
Cost Item | Reflash-First | Air-First (60%) | Full Air (100%) | Unit
PCBA by Air | 0 | 35020 | 58368 | units
PCBA by Sea | 0 | 0 | 0 | units
PCBA Reflashed (from May 6) | 370000 | 370000 | 370000 | units
Air freight extra cost | 0 | 70040 | 116736 | USD
Sea freight extra cost | 0 | 0 | 0 | USD
Reflash equipment cost | 0 | 0 | 0 | USD (assumed $0)
TOTAL logistics cost | 0 | 70040 | 116736 | USD
SKU A demand | 51684 | 51684 | 51684 | FG units
SKU A planned | 22500 | 40010 | 51684 | FG units
SKU A shortage | 29184 | 11674 | 0 | FG units
SKU A shortage % | 56.5% | 22.6% | 0.0%
Revenue impact (A shortage * $105) | 3064320 | 1225770 | 0 | USD lost revenue
Net scenario cost | -3064320 | -1155730 | 116736 | USD (cost - saved rev)
Service level recovery | 0% | 60% | 100%
Recommendation |  | SELECTED

## Customer_Service_Priority
Market | SKU | Priority | Ship Request | Demand Qty | Revenue Proxy (USD) | Strategic Importance | Partial Ship OK? | Delay Tolerance | Service Target | Allocation Rank | Baseline Shortage | Scenario Shortage | Impact
US | F | 2 | 2026-05-01 | 588 | 52920 | MEDIUM | Yes | Medium | Best effort | 1 | 0 | 0 | SAME
US | A | 1 | 2026-05-08 | 684 | 71820 | HIGH | Limited | Low | On-time | 2 | 11000 | 0 | BETTER
Australia | E | 1 | 2026-05-08 | 472 | 14160 | HIGH | Limited | Low | On-time | 3 | 698 | 0 | BETTER
US | F | 2 | 2026-05-08 | 4028 | 362520 | MEDIUM | Yes | Medium | Best effort | 4 | 4500 | 0 | BETTER
US | A | 1 | 2026-05-15 | 20000 | 2100000 | HIGH | Limited | Low | On-time | 5 | 0 | 0 | SAME
US | B | 2 | 2026-05-15 | 5502 | 302610 | MEDIUM | Yes | Medium | Best effort | 6 | 0 | 0 | SAME
UK | C | 1 | 2026-05-15 | 4320 | 345600 | HIGH | Limited | Low | On-time | 7 | 11782 | 0 | BETTER
UK | D | 2 | 2026-05-15 | 2430 | 97200 | MEDIUM | Yes | Medium | Best effort | 8 | 0 | 2430 | WORSE
Australia | E | 1 | 2026-05-15 | 300 | 9000 | HIGH | Limited | Low | On-time | 9 | 0 | 0 | SAME
US | F | 2 | 2026-05-15 | 4200 | 378000 | MEDIUM | Yes | Medium | Best effort | 10 | 0 | 0 | SAME
US | A | 1 | 2026-05-22 | 20000 | 2100000 | HIGH | Limited | Low | On-time | 11 | 0 | 674 | WORSE
US | B | 2 | 2026-05-22 | 15658 | 861190 | MEDIUM | Yes | Medium | Best effort | 12 | 8865 | 0 | BETTER
UK | C | 1 | 2026-05-22 | 8370 | 669600 | HIGH | Limited | Low | On-time | 13 | 0 | 0 | SAME
UK | D | 2 | 2026-05-22 | 9990 | 399600 | MEDIUM | Yes | Medium | Best effort | 14 | 5840 | 9990 | WORSE
Australia | E | 1 | 2026-05-22 | 698 | 20940 | HIGH | Limited | Low | On-time | 15 | 0 | 0 | SAME
US | F | 2 | 2026-05-22 | 3802 | 342180 | MEDIUM | Yes | Medium | Best effort | 16 | 0 | 588 | WORSE
US | A | 1 | 2026-05-29 | 11000 | 1155000 | HIGH | Limited | Low | On-time | 17 | 0 | 11000 | WORSE
US | B | 2 | 2026-05-29 | 8865 | 487575 | MEDIUM | Yes | Medium | Best effort | 18 | 0 | 2535 | WORSE
UK | C | 1 | 2026-05-29 | 11782 | 942560 | HIGH | Limited | Low | On-time | 19 | 0 | 1981 | WORSE
UK | D | 2 | 2026-05-29 | 5840 | 233600 | MEDIUM | Yes | Medium | Best effort | 20 | 0 | 5840 | WORSE
US | F | 2 | 2026-05-29 | 4500 | 405000 | MEDIUM | Yes | Medium | Best effort | 21 | 0 | 4500 | WORSE

## Validation_Checks
Check # | Description | Expected | Actual | Status
1 | A production * 2 <= total usable PCBA | <= 405,020 | 80,020 | PASS
2 | No negative usable PCBA balance | 0 violations | 0 violations | PASS
3 | No fixture overload per day | 0 overloads | 0 overloads | PASS
4 | Inventory continuity (EndInv[t-1] = BegInv[t]) | All match | Checked | PASS
5 | Shortage = Demand - Planned (net of inventory) | Consistent | Tot dem=143,029 plan=103,491 short=39,538 | PASS
6 | Horizon = 15/04/2026 to 15/05/2026 | 2026-04-15 to 2026-05-15 | 2026-04-15 to 2026-05-15 | PASS
7 | A shortage <= 11674 (60% recovery cap) | <= 11,674 | 11,674 | PASS
8 | No external links in this workbook | 0 | 0 (new build) | PASS

## Fix_Log
# | Action | Detail | Source
1 | NEW SHEET: Scenario_Input | All scenario assumptions in one place | Case study + BOM sheet
2 | NEW SHEET: PCBA_Recovery_Plan | Daily PCBA availability timeline with air/reflash/sea | Solver output
3 | NEW SHEET: Scenario_PP | Full production plan with PCBA gating + inventory continuity | LP solver (PuLP)
4 | NEW SHEET: Scenario_Cost_Analysis | 3-way cost comparison: Reflash-first vs Air-60% vs Full Air | Solver + assumptions
5 | NEW SHEET: Customer_Service_Priority | Market/SKU priority allocation under shortage | Input sheet priorities
6 | NEW SHEET: Validation_Checks | 8 automated checks on PP integrity | Calculated
7 | NEW SHEET: Fix_Log | This change log
8 | COPIED: Original sheets preserved | All original sheets from raw file copied as-is | SCM_round2.1_new.xlsx
9 | REMOVED: External links | New workbook built from scratch; no external links possible
10 | ASSUMPTION: Reflash capacity | Unlimited once equipment arrives (all 370K available) | Reasonable: 370K >> 45K needed
11 | ASSUMPTION: Reflash cost | $0 extra (equipment cost not quantified) | Case study silent on cost
12 | ASSUMPTION: Sea extra cost | $0 (baseline shipping) | Only air has +$2 premium
13 | ASSUMPTION: Opening FG inventory | 0 for all SKUs | Input sheet row 5
14 | DATA: BOM usage A->RM04 | 2 PCBA per FG | BOM & Inventory R8
15 | DATA: PCBA stock | 340,000 + 30,000 PO = 370,000 on hold | BOM & Inventory R8
16 | DATA: SKU priorities | A>B (P1>P2), C>D, E>F | Input sheet col G
17 | DATA: Fixture caps | 123AB=15000/wk, 456CD=5000/wk, 789EF=3000/wk | Input sheet col D
18 | LIMITATION: No detailed customer data | Service priority by market/SKU, not individual customer | Data not available
19 | LIMITATION: Reflash rate unknown | Assumed instant; real rate may reduce Phase 2 capacity | Not specified in case
20 | DECISION: 60% recovery chosen | A shortage capped at 11,674; air cost = $70,040 | recovery_analysis.py

## ORIG_input
Backward MPS Input
Planning logic | Backward scheduling with shared fixture cap lock by fixture-week
Production can start from | 2026-04-13
Demand source | SCM_round2.1.xlsx / demand_matrix
Opening FG assumption | 0
Shortage rule | Allowed; not forced to zero; capacity shared by fixture-week with priority A>B, C>D, E>F
SKU | Description | Fixture | Weekly Capacity | Opening FG | Storage Cap | Priority | Week | A | B | C | D | E | F
A | 2026 Automatic Robot ver | 123AB | 15000 | 0 | 15000 | 1 | 2026-04-13 | 0 | 0 | 0 | 0 | 0 | 0
B | 2025 Barbie ver colorful | 123AB | 15000 | 0 | 15000 | 2 | 2026-04-20 | 0 | 0 | 0 | 0 | 0 | 588
C | 2026 Castle & Farm Blocks | 456CD | 5000 | 0 | 5000 | 1 | 2026-04-27 | 684 | 0 | 0 | 0 | 472 | 4028
D | 2026 Animal Animation Book | 456CD | 5000 | 0 | 5000 | 2 | 2026-05-04 | 20000 | 5502 | 4320 | 2430 | 300 | 4200
E | 2026 Scooter ver | 789EF | 3000 | 0 | 3000 | 1 | 2026-05-11 | 20000 | 15658 | 8370 | 9990 | 698 | 3802
F | 2025 Fantasy Spaceship Model DIY kits | 789EF | 3000 | 0 | 3000 | 2 | 2026-05-18 | 11000 | 8865 | 11782 | 5840 | 0 | 4500
[7 empty] | 2026-05-25 | 13000 | 2146 | 10524 | 8100 | 300 | 4200
[7 empty] | 2026-06-01 | 13773 | 7123 | 3240 | 1001 | 0 | 4500
[7 empty] | 2026-06-08 | 7058 | 5309 | 6442 | 2471 | 0 | 4500
[7 empty] | 2026-06-15 | 2040 | 5309 | 8802 | 3458 | 300 | 2200
[7 empty] | 2026-06-22 | 3541 | 3000 | 7695 | 500 | 0 | 5000
[7 empty] | 2026-06-29 | 12041 | 3000 | 2500 | 500 | 700 | 4300
[7 empty] | 2026-07-06 | 12040 | 3000 | 2500 | 500 | 300 | 4700
[7 empty] | 2026-07-13 | 0 | 3000 | 2500 | 500 | 300 | 4746
[7 empty] | 2026-07-20 | 0 | 2400 | 1000 | 0 | 300 | 4300
[7 empty] | 2026-07-27 | 27760 | 2400 | 1000 | 0 | 0 | 476
[7 empty] | 2026-08-03 | 26486 | 0 | 1000 | 400 | 0 | 1298
[7 empty] | 2026-08-10 | 4248 | 2400 | 1000 | 0 | 300 | 1300
[7 empty] | 2026-08-17 | 4248 | 2400 | 1000 | 0 | 0 | 1298
[7 empty] | 2026-08-24 | 4249 | 3750 | 750 | 400 | 0 | 1506
[7 empty] | 2026-08-31 | 4248 | 3750 | 750 | 0 | 300 | 1506
[7 empty] | 2026-09-07 | 2391 | 3750 | 750 | 400 | 0 | 1506
[7 empty] | 2026-09-14 | 2392 | 3750 | 750 | 0 | 0 | 1506
[7 empty] | 2026-09-21 | 2391 | 3000 | 600 | 360 | 0 | 1446
[7 empty] | 2026-09-28 | 2392 | 3000 | 600 | 360 | 300 | 0
[7 empty] | 2026-10-05 | 16017 | 3000 | 600 | 360 | 0 | 0
[7 empty] | 2026-10-12 | 16017 | 3000 | 600 | 360 | 0 | 1448
[7 empty] | 2026-10-19 | 16016 | 3000 | 600 | 360 | 0 | 1448
[7 empty] | 2026-10-26 | 16017 | 6250 | 500 | 1000 | 0 | 1448
[7 empty] | 2026-11-02 | 4281 | 6250 | 500 | 1000 | 300 | 1754
[7 empty] | 2026-11-09 | 4282 | 6250 | 500 | 1000 | 0 | 1756
[7 empty] | 2026-11-16 | 4281 | 6250 | 500 | 1000 | 0 | 1756
[7 empty] | 2026-11-23 | 4282 | 6250 | 3000 | 1250 | 0 | 1756
[7 empty] | 2026-11-30 | 4281 | 6250 | 3000 | 1250 | 300 | 1928
[7 empty] | 2026-12-07 | 8326 | 6250 | 3000 | 1250 | 0 | 1930
[7 empty] | 2026-12-14 | 8325 | 6250 | 3000 | 1250 | 0 | 1928

## ORIG_demand_matrix
Week | A | B | C | D | E | F
2026-04-20 | 0 | 0 | 0 | 0 | 0 | 588
2026-04-27 | 684 | 0 | 0 | 0 | 472 | 4028
2026-05-04 | 20000 | 5502 | 4320 | 2430 | 300 | 4200
2026-05-11 | 20000 | 15658 | 8370 | 9990 | 698 | 3802
2026-05-18 | 11000 | 8865 | 11782 | 5840 | 0 | 4500
2026-05-25 | 13000 | 2146 | 10524 | 8100 | 300 | 4200
2026-06-01 | 13773 | 7123 | 3240 | 1001 | 0 | 4500
2026-06-08 | 7058 | 5309 | 6442 | 2471 | 0 | 4500
2026-06-15 | 2040 | 5309 | 8802 | 3458 | 300 | 2200
2026-06-22 | 3541 | 3000 | 7695 | 500 | 0 | 5000
2026-06-29 | 12041 | 3000 | 2500 | 500 | 700 | 4300
2026-07-06 | 12040 | 3000 | 2500 | 500 | 300 | 4700
2026-07-13 | 0 | 3000 | 2500 | 500 | 300 | 4746
2026-07-20 | 0 | 2400 | 1000 | 0 | 300 | 4300
2026-07-27 | 27760 | 2400 | 1000 | 0 | 0 | 476
2026-08-03 | 26486 | 0 | 1000 | 400 | 0 | 1298
2026-08-10 | 4248 | 2400 | 1000 | 0 | 300 | 1300
2026-08-17 | 4248 | 2400 | 1000 | 0 | 0 | 1298
2026-08-24 | 4249 | 3750 | 750 | 400 | 0 | 1506
2026-08-31 | 4248 | 3750 | 750 | 0 | 300 | 1506
2026-09-07 | 2391 | 3750 | 750 | 400 | 0 | 1506
2026-09-14 | 2392 | 3750 | 750 | 0 | 0 | 1506
2026-09-21 | 2391 | 3000 | 600 | 360 | 0 | 1446
2026-09-28 | 2392 | 3000 | 600 | 360 | 300 | 0
2026-10-05 | 16017 | 3000 | 600 | 360 | 0 | 0
2026-10-12 | 16017 | 3000 | 600 | 360 | 0 | 1448
2026-10-19 | 16016 | 3000 | 600 | 360 | 0 | 1448
2026-10-26 | 16017 | 6250 | 500 | 1000 | 0 | 1448
2026-11-02 | 4281 | 6250 | 500 | 1000 | 300 | 1754
2026-11-09 | 4282 | 6250 | 500 | 1000 | 0 | 1756
2026-11-16 | 4281 | 6250 | 500 | 1000 | 0 | 1756
2026-11-23 | 4282 | 6250 | 3000 | 1250 | 0 | 1756
2026-11-30 | 4281 | 6250 | 3000 | 1250 | 300 | 1928
2026-12-07 | 8326 | 6250 | 3000 | 1250 | 0 | 1930
2026-12-14 | 8325 | 6250 | 3000 | 1250 | 0 | 1928

## ORIG_BOM_n_Inventory
No. | Model number | Component number | Description | Vendor location | BOM usage | Leadtime | Stock | Pending PO | U/P (USD/ uom) | UOM
1 | A | RM01 | Packaging label | Local | 1 | 7 | 588 | 0 | 0.2 | pc
2 | A | RM02 | Packaging carton | Local | 0.25 | 14 | 1443 | 0 | 4 | Pc
3 | A | RM03 | Common plastic | Local | 1 | 21 | 42524 | 0 | 5 | Kg
4 | A | RM04 | PCBA | Oversea | 2 | 140 | 340000 | 30000 | 15 | pc
5 | A | RM05 | Charger | Oversea | 1 | 70 | 90000 | 0 | 25 | pc
6 | B | RM01 | Packaging label | Local | 1 | 7 | 588 | 0 | 0.2 | pc
7 | B | RM02 | Packaging carton | Local | 0.25 | 14 | 1443 | 0 | 4 | Pc
8 | B | RM03 | Common plastic | Local | 1 | 21 | 42524 | 0 | 5 | Kg
9 | B | RM06 | Fabric | Oversea | 2.5 | 35 | 76000 | 0 | 10 | m
10 | B | RM07 | Industrial color | Oversea | 1.5 | 42 | 50000 | 0 | 7 | gr
11 | C | RM01 | Packaging label | Local | 1 | 7 | 588 | 0 | 0.2 | pc
12 | C | RM02 | Packaging carton | Local | 0.5 | 14 | 2886 | 0 | 4 | Pc
13 | C | RM03 | Common plastic | Local | 1 | 21 | 42524 | 0 | 5 | Kg
14 | C | RM08 | Special Resin | Oversea | 3 | 63 | 123000 | 38000 | 7 | kg
15 | C | RM09 | Wooden | Oversea | 0.5 | 28 | 6500 | 0 | 40 | Cbm
16 | D | RM01 | Packaging label | Local | 1 | 7 | 588 | 0 | 0.2 | pc
17 | D | RM02 | Packaging carton | Local | 0.25 | 14 | 1443 | 0 | 4 | Pc
18 | D | RM03 | Common plastic | Local | 1 | 21 | 42524 | 0 | 5 | Kg
19 | D | RM10 | Battery | Oversea | 2 | 77 | 60000 | 5000 | 10 | pc
20 | D | RM11 | Glue | Oversea | 1.5 | 21 | 100000 | 0 | 0.2 | gr
21 | E | RM01 | Packaging label | Local | 1 | 7 | 588 | 0 | 0.2 | pc
22 | E | RM02 | Packaging carton | Local | 0.5 | 14 | 2886 | 0 | 4 | Pc
23 | E | RM03 | Common plastic | Local | 1 | 21 | 42524 | 0 | 5 | Kg
24 | E | RM12 | Steel metal | Oversea | 3 | 56 | 5500 | 0 | 5 | m
25 | E | RM13 | Wheel | Oversea | 4 | 35 | 6000 | 1000 | 1 | pc
26 | F | RM01 | Packaging label | Local | 1 | 7 | 588 | 0 | 0.2 | pc
27 | F | RM02 | Packaging carton | Local | 0.125 | 14 | 721.5 | 0 | 4 | Pc
28 | F | RM03 | Common plastic | Local | 1 | 21 | 42524 | 0 | 5 | Kg
29 | F | RM14 | Solar pannel | Oversea | 5 | 63 | 130000 | 0 | 10 | pc
30 | F | RM15 | Cell | Oversea | 2 | 49 | 20000 | 21000 | 6 | pc

## ORIG_FGs_n_Log_information
Item name | Des | Packing size (pcs/ carton) | CBM (100 cartons) | Ex. Work price (Usd/ pc) | Market
A | 2026 Automatic Robot ver | 4 | 1 | 105 | US
B | 2025 Barbie ver colorful | 4 | 0.625 | 55 | US
C | 2026 Castle & Farm Blocks | 2 | 1 | 80 | UK
D | 2026 Animal Animation Book | 4 | 0.625 | 40 | UK
E | 2026 Scooter ver | 2 | 0.625 | 30 | Australia
F | 2025 Fantasy Spaceship Model DIY kits | 8 | 0.78125 | 90 | US
Coporate Ocean frieght charge
FCL | US | UK | AU | Max load CBM / container
40" | 5200 | 4200 | 2000 | 65
20" | 3000 | 2500 | 1100 | 28
LT (day) | 50 | 40 | 25
LCL
per CBM | 200 | 70 | 35
LT (day) | 55 | 45 | 30
Airfreigh , follow forwarder website at demand date

## ORIG_Production_plan
Production Planning | [8 empty] | Calendar Buckets & Available Capacity (6 workdays/week, Sunday off)
[9 empty] | Bucket | Start | End | Workdays | Workdays/6 | Notes
Start date | 2026-04-15 | [7 empty] | B1 | 2026-04-15 | 2026-04-18 | 4 | 0.67 | Mon–Sat; Sunday off
End date | 2026-05-15 | [7 empty] | B2 | 2026-04-20 | 2026-04-25 | 6 | 1 | Mon–Sat; Sunday off
Workdays / week | 6 | [7 empty] | B3 | 2026-04-27 | 2026-05-02 | 6 | 1 | Mon–Sat; Sunday off
Shifts / day | 2 | [7 empty] | B4 | 2026-05-04 | 2026-05-09 | 6 | 1 | Mon–Sat; Sunday off
Lead time min (days) | 7 | [7 empty] | B5 | 2026-05-11 | 2026-05-15 | 5 | 0.83 | Mon–Sat; Sunday off
Lead time max (days) | 14
Note | Factory runs 2 shifts/day, 6 days/week (Sunday off). Plan buckets follow Mon–Sat weeks.
Overall
Total workdays in horizon | 27
Theoretical shipment request estimated by lead time | 22/04 - 29/05
Demand Aggregated for Production Horizon (15.4-15.5) | [10 empty] | Fixture | Weekly capacity | B1 | B2 | B3 | B4 | B5 | Total capacity (horizon)
[11 empty] | 123AB | 15000 | 10000 | 15000 | 15000 | 15000 | 12500 | 67500
SKU | Description | Market | Product group | Fixture | Weekly capacity | Ship request | Demand quantity | Earliest production date (Ship-LeadMax) | Latest production date (Ship-LeadMin) |  | 456CD | 5000 | 3333.3333 | 5000 | 5000 | 5000 | 4166.6667 | 22500
A | 2026 Automatic Robot ver | US | Electronic Toy | 123AB | 15000 | 2026-05-08 | #VALUE! | 2026-04-24 | 2026-05-01 |  | 789EF | 3000 | 2000 | 3000 | 3000 | 3000 | 2500 | 13500
A | 2026 Automatic Robot ver | US | Electronic Toy | 123AB | 15000 | 2026-05-15 | #VALUE! | 2026-05-01 | 2026-05-08
A | 2026 Automatic Robot ver | US | Electronic Toy | 123AB | 15000 | 2026-05-22 | #VALUE! | 2026-05-08 | 2026-05-15
A | 2026 Automatic Robot ver | US | Electronic Toy | 123AB | 15000 | 2026-05-29 | #VALUE! | 2026-05-15 | 2026-05-22
B | 2025 Barbie ver colorful | US | Doll | 123AB | 15000 | 2026-05-15 | #VALUE! | 2026-05-01 | 2026-05-08
B | 2025 Barbie ver colorful | US | Doll | 123AB | 15000 | 2026-05-22 | #VALUE! | 2026-05-08 | 2026-05-15
B | 2025 Barbie ver colorful | US | Doll | 123AB | 15000 | 2026-05-29 | #VALUE! | 2026-05-15 | 2026-05-22
C | 2026 Castle & Farm Blocks | UK | Building & Construction Toy | 456CD | 5000 | 2026-05-15 | #VALUE! | 2026-05-01 | 2026-05-08
C | 2026 Castle & Farm Blocks | UK | Building & Construction Toy | 456CD | 5000 | 2026-05-22 | #VALUE! | 2026-05-08 | 2026-05-15
C | 2026 Castle & Farm Blocks | UK | Building & Construction Toy | 456CD | 5000 | 2026-05-29 | #VALUE! | 2026-05-15 | 2026-05-22
D | 2026 Animal Animation Book | UK | Educational Toy | 456CD | 5000 | 2026-05-15 | #VALUE! | 2026-05-01 | 2026-05-08
D | 2026 Animal Animation Book | UK | Educational Toy | 456CD | 5000 | 2026-05-22 | #VALUE! | 2026-05-08 | 2026-05-15
D | 2026 Animal Animation Book | UK | Educational Toy | 456CD | 5000 | 2026-05-29 | #VALUE! | 2026-05-15 | 2026-05-22
E | 2026 Scooter ver | Australia | Outdoor & Sports Toy | 789EF | 3000 | 2026-05-08 | #VALUE! | 2026-04-24 | 2026-05-01
E | 2026 Scooter ver | Australia | Outdoor & Sports Toy | 789EF | 3000 | 2026-05-15 | #VALUE! | 2026-05-01 | 2026-05-08
E | 2026 Scooter ver | Australia | Outdoor & Sports Toy | 789EF | 3000 | 2026-05-22 | #VALUE! | 2026-05-08 | 2026-05-15
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 3000 | 2026-05-01 | #VALUE! | 2026-04-17 | 2026-04-24
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 3000 | 2026-05-08 | #VALUE! | 2026-04-24 | 2026-05-01
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 3000 | 2026-05-15 | #VALUE! | 2026-05-01 | 2026-05-08
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 3000 | 2026-05-22 | #VALUE! | 2026-05-08 | 2026-05-15
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 3000 | 2026-05-29 | #VALUE! | 2026-05-15 | 2026-05-22
Production Plan (Daily workday view)
SKU | Description | Market | Product group | Fixture | Weekly cap | Ship request | Demand quantity | Earliest production date | Latest production date | Week 1 |  |  |  | Week 2 | [5 empty] | Week 3 | [5 empty] | Week 4 | [5 empty] | Week 5 |  |  |  |  | Planned total | Shortage | Risk | Late qty | Horizon status
[10 empty] | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 3000 | 2026-05-01 | 588 | 2026-04-17 | 2026-04-24 | 0 | 0 | 0 | 0 | 98 | 98 | 98 | 98 | 98 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 588 | 0 | LATE | 98 | WITHIN_HORIZON
A | 2026 Automatic Robot ver | US | Electronic Toy | 123AB | 15000 | 2026-05-08 | 684 | 2026-04-24 | 2026-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316.058 | 316.058 | 316.058 | 316.058 | 316.058 | 316.058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1896.3478 | 0 | LATE | 316.058 | WITHIN_HORIZON
E | 2026 Scooter ver | Australia | Outdoor & Sports Toy | 789EF | 3000 | 2026-05-08 | 472 | 2026-04-24 | 2026-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 172 | SHORTAGE + LATE | 50 | WITHIN_HORIZON
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 3000 | 2026-05-08 | 4028 | 2026-04-24 | 2026-05-01 | 308.8 | 308.8 | 308.8 | 308.8 | 127.4667 | 127.4667 | 127.4667 | 127.4667 | 127.4667 | 127.4667 | 500 | 500 | 500 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | LATE | 500 | WITHIN_HORIZON
A | 2026 Automatic Robot ver | US | Electronic Toy | 123AB | 15000 | 2026-05-15 | 20000 | 2026-05-01 | 2026-05-08 | 0 | 0 | 0 | 0 | 462.2667 | 462.2667 | 462.2667 | 462.2667 | 462.2667 | 462.2667 | 2183.942 | 2183.942 | 2183.942 | 2183.942 | 2183.942 | 2183.942 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 30877.2522 | 0 | LATE | 2500 | WITHIN_HORIZON
B | 2025 Barbie ver colorful | US | Doll | 123AB | 15000 | 2026-05-15 | 5502 | 2026-05-01 | 2026-05-08 | 0 | 0 | 0 | 0 | 917 | 917 | 917 | 917 | 917 | 917 | 188.1339 | 188.1339 | 188.1339 | 188.1339 | 188.1339 | 188.1339 | 458.1182 | 458.1182 | 458.1182 | 458.1182 | 458.1182 | 458.1182 | 270.7479 | 270.7479 | 270.7479 | 270.7479 | 270.7479 | 10733.2521 | 0 | LATE | 1811.8576 | WITHIN_HORIZON
C | 2026 Castle & Farm Blocks | UK | Building & Construction Toy | 456CD | 5000 | 2026-05-15 | 4320 | 2026-05-01 | 2026-05-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | LATE | 833.3333 | WITHIN_HORIZON
D | 2026 Animal Animation Book | UK | Educational Toy | 456CD | 5000 | 2026-05-15 | 2430 | 2026-05-01 | 2026-05-08 | 0 | 0 | 0 | 0 | 152.7833 | 152.7833 | 152.7833 | 152.7833 | 152.7833 | 152.7833 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 110.8981 | 110.8981 | 110.8981 | 110.8981 | 110.8981 | 110.8981 | 110.8981 | 110.8981 | 110.8981 | 110.8981 | 110.8981 | 7136.5795 | 0 | LATE | 665.3888 | WITHIN_HORIZON
E | 2026 Scooter ver | Australia | Outdoor & Sports Toy | 789EF | 3000 | 2026-05-15 | 300 | 2026-05-01 | 2026-05-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116.3333 | 116.3333 | 116.3333 | 116.3333 | 116.3333 | 116.3333 | 0 | 0 | 0 | 0 | 0 | 698 | 0 | LATE | 116.3333 | WITHIN_HORIZON
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 3000 | 2026-05-15 | 4200 | 2026-05-01 | 2026-05-08 | 191.2 | 191.2 | 191.2 | 191.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 500 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 3764.8 | 435.2 | SHORTAGE + LATE | 500 | WITHIN_HORIZON
A | 2026 Automatic Robot ver | US | Electronic Toy | 123AB | 15000 | 2026-05-22 | 20000 | 2026-05-08 | 2026-05-15 | 193.9 | 193.9 | 193.9 | 193.9 | 1120.7333 | 1120.7333 | 1120.7333 | 1120.7333 | 1120.7333 | 1120.7333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1833.3333 | 1833.3333 | 1833.3333 | 1833.3333 | 1833.3333 | 16666.6667 | 3333.3333 | SHORTAGE | 0 | WITHIN_HORIZON
B | 2025 Barbie ver colorful | US | Doll | 123AB | 15000 | 2026-05-22 | 15658 | 2026-05-08 | 2026-05-15 | 2306.1 | 2306.1 | 2306.1 | 2306.1 | 0 | 0 | 0 | 0 | 0 | 0 | 535.4054 | 535.4054 | 535.4054 | 535.4054 | 535.4054 | 535.4054 | 1303.7469 | 1303.7469 | 1303.7469 | 1303.7469 | 1303.7469 | 1303.7469 | 770.5144 | 770.5144 | 770.5144 | 770.5144 | 770.5144 | 24111.8856 | 0 | OK | 0 | WITHIN_HORIZON
C | 2026 Castle & Farm Blocks | UK | Building & Construction Toy | 456CD | 5000 | 2026-05-22 | 8370 | 2026-05-08 | 2026-05-15 | 30 | 30 | 30 | 30 | 680.55 | 680.55 | 680.55 | 680.55 | 680.55 | 680.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 833.3333 | 8369.9667 | 0.033333 | SHORTAGE | 0 | WITHIN_HORIZON
D | 2026 Animal Animation Book | UK | Educational Toy | 456CD | 5000 | 2026-05-22 | 9990 | 2026-05-08 | 2026-05-15 | 803.325 | 803.325 | 803.325 | 803.325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455.9146 | 455.9146 | 455.9146 | 455.9146 | 455.9146 | 455.9146 | 455.9146 | 455.9146 | 455.9146 | 455.9146 | 455.9146 | 8228.3602 | 1761.6398 | SHORTAGE | 0 | WITHIN_HORIZON
E | 2026 Scooter ver | Australia | Outdoor & Sports Toy | 789EF | 3000 | 2026-05-22 | 698 | 2026-05-08 | 2026-05-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139.6 | 139.6 | 139.6 | 139.6 | 139.6 | 698 | 0 | OK | 0 | WITHIN_HORIZON
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 3000 | 2026-05-22 | 3802 | 2026-05-08 | 2026-05-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 500 | 500 | 500 | 2500 | 1302 | SHORTAGE | 0 | WITHIN_HORIZON
A | 2026 Automatic Robot ver | US | Electronic Toy | 123AB | 15000 | 2026-05-29 | 11000 | 2026-05-15 | 2026-05-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 | OUT_OF_HORIZON | 0 | PARTIAL_HORIZON
B | 2025 Barbie ver colorful | US | Doll | 123AB | 15000 | 2026-05-29 | 8865 | 2026-05-15 | 2026-05-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 303.1274 | 303.1274 | 303.1274 | 303.1274 | 303.1274 | 303.1274 | 738.1349 | 738.1349 | 738.1349 | 738.1349 | 738.1349 | 738.1349 | 436.2377 | 436.2377 | 436.2377 | 436.2377 | 436.2377 | 8428.7623 | 436.2377 | OUT_OF_HORIZON | 0 | PARTIAL_HORIZON
C | 2026 Castle & Farm Blocks | UK | Building & Construction Toy | 456CD | 5000 | 2026-05-29 | 11782 | 2026-05-15 | 2026-05-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11782 | OUT_OF_HORIZON | 0 | PARTIAL_HORIZON
D | 2026 Animal Animation Book | UK | Educational Toy | 456CD | 5000 | 2026-05-29 | 5840 | 2026-05-15 | 2026-05-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 266.5206 | 266.5206 | 266.5206 | 266.5206 | 266.5206 | 266.5206 | 266.5206 | 266.5206 | 266.5206 | 266.5206 | 266.5206 | 2931.7269 | 2908.2731 | OUT_OF_HORIZON | 0 | PARTIAL_HORIZON
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 3000 | 2026-05-29 | 4500 | 2026-05-15 | 2026-05-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | OUT_OF_HORIZON | 0 | PARTIAL_HORIZON

## Scenario_MPS
SKU | Fixture | Week | Weekly Capacity | Total Demand | Beginning FG Inv | Storage Cap | Carryover Needed | Net Required | Planned Production | Ending FG Inv | Shortage | ATP | Capacity Load % | Planner Note
A | 123AB | 2026-04-13 | 15000 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | PCBA limited - air only
A | 123AB | 2026-04-20 | 15000 | 0 | 0 | 15000 | 0 | 0 | 5510 | 5510 | 0 | 5510 | 36.73% | PCBA limited - air only
A | 123AB | 2026-04-27 | 15000 | 684 | 5510 | 15000 | 4826 | 0 | 7000 | 11826 | 0 | 11826 | 46.67% | PCBA limited - air only
A | 123AB | 2026-05-04 | 15000 | 20000 | 11826 | 15000 | 0 | 8174 | 15000 | 6826 | 0 | 6826 | 100% | PCBA reflash available
A | 123AB | 2026-05-11 | 15000 | 20000 | 6826 | 15000 | 0 | 13174 | 12500 | 0 | 674 | 0 | 83.33% | SHORTAGE: 674
B | 123AB | 2026-04-13 | 15000 | 0 | 0 | 15000 | 0 | 0 | 10000 | 10000 | 0 | 10000 | 66.67%
B | 123AB | 2026-04-20 | 15000 | 0 | 10000 | 15000 | 10000 | 0 | 9490 | 19490 | 0 | 19490 | 63.27%
B | 123AB | 2026-04-27 | 15000 | 0 | 19490 | 15000 | 19490 | 0 | 8000 | 27490 | 0 | 27490 | 53.33%
B | 123AB | 2026-05-04 | 15000 | 5502 | 27490 | 15000 | 21988 | 0 | 0 | 21988 | 0 | 21988 | 0%
B | 123AB | 2026-05-11 | 15000 | 15658 | 21988 | 15000 | 6330 | 0 | 0 | 6330 | 0 | 6330 | 0%
C | 456CD | 2026-04-13 | 5000 | 0 | 0 | 5000 | 0 | 0 | 3332 | 3332 | 0 | 3332 | 66.64%
C | 456CD | 2026-04-20 | 5000 | 0 | 3332 | 5000 | 3332 | 0 | 4998 | 8330 | 0 | 8330 | 99.96%
C | 456CD | 2026-04-27 | 5000 | 0 | 8330 | 5000 | 8330 | 0 | 4998 | 13328 | 0 | 13328 | 99.96%
C | 456CD | 2026-05-04 | 5000 | 4320 | 13328 | 5000 | 9008 | 0 | 4998 | 14006 | 0 | 14006 | 99.96%
C | 456CD | 2026-05-11 | 5000 | 8370 | 14006 | 5000 | 5636 | 0 | 4165 | 9801 | 0 | 9801 | 83.3%
D | 456CD | 2026-04-13 | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
D | 456CD | 2026-04-20 | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
D | 456CD | 2026-04-27 | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
D | 456CD | 2026-05-04 | 5000 | 2430 | 0 | 5000 | 0 | 2430 | 0 | 0 | 2430 | 0 | 0% | SHORTAGE: 2,430
D | 456CD | 2026-05-11 | 5000 | 9990 | 0 | 5000 | 0 | 9990 | 0 | 0 | 9990 | 0 | 0% | SHORTAGE: 9,990
E | 789EF | 2026-04-13 | 3000 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
E | 789EF | 2026-04-20 | 3000 | 0 | 0 | 3000 | 0 | 0 | 500 | 500 | 0 | 500 | 16.67%
E | 789EF | 2026-04-27 | 3000 | 472 | 500 | 3000 | 28 | 0 | 970 | 998 | 0 | 998 | 32.33%
E | 789EF | 2026-05-04 | 3000 | 300 | 998 | 3000 | 698 | 0 | 0 | 698 | 0 | 698 | 0%
E | 789EF | 2026-05-11 | 3000 | 698 | 698 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
F | 789EF | 2026-04-13 | 3000 | 0 | 0 | 3000 | 0 | 0 | 2000 | 2000 | 0 | 2000 | 66.67%
F | 789EF | 2026-04-20 | 3000 | 588 | 2000 | 3000 | 1412 | 0 | 2500 | 3912 | 0 | 3912 | 83.33%
F | 789EF | 2026-04-27 | 3000 | 4028 | 3912 | 3000 | 0 | 116 | 2030 | 1914 | 0 | 1914 | 67.67%
F | 789EF | 2026-05-04 | 3000 | 4200 | 1914 | 3000 | 0 | 2286 | 3000 | 714 | 0 | 714 | 100%
F | 789EF | 2026-05-11 | 3000 | 3802 | 714 | 3000 | 0 | 3088 | 2500 | 0 | 588 | 0 | 83.33% | SHORTAGE: 588

## Scenario_MRP
Scenario MRP
Items | A | B | C | D | E | F | RM01 | RM02 | RM03 | RM04 | RM05 | RM06 | RM07 | RM08 | RM09 | RM10 | RM11 | RM12 | RM13 | RM14 | RM15
Lead time | 1-2 weeks | 1-2 weeks | 1-2 weeks | 1-2 weeks | 1-2 weeks | 1-2 weeks | 7 | 14 | 21 | 140 | 70 | 35 | 42 | 63 | 28 | 77 | 21 | 56 | 35 | 63 | 49
Beginning inventory | 0 | 0 | 0 | 0 | 0 | 0 | 588 | 1443 | 42524 | 340000 | 90000 | 76000 | 50000 | 123000 | 6500 | 60000 | 100000 | 5500 | 6000 | 130000 | 20000
Scheduled receipts | [9 empty] | 30000 |  |  |  | 38000 |  | 5000 |  |  | 1000 |  | 21000
Item RM01 | LLC: 1 | Packaging label
| LT: 1 wk | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11
Gross requirements |  | 15332 | 22998 | 22998 | 22998 | 19165
Scheduled receipts
Projected on hand | 588 | -14744 | -37742 | -60740 | -83738 | -102903
Net requirements |  | 14744 | 8254 | 14744 | 8254 | 10911
Planned order receipts |  | 14744 | 8254 | 14744 | 8254 | 10911
Planned order releases |  | 8254 | 14744 | 8254 | 10911
Item RM02 | LLC: 1 | Packaging carton
| LT: 2 wk | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11
Gross requirements |  | 4416 | 6810 | 6987 | 6624 | 5519
Scheduled receipts
Projected on hand | 1443 | -2973 | -9783 | -16770 | -23394 | -28913
Net requirements |  | 2973 | 3837 | 3150 | 3474 | 2045
Planned order receipts |  | 2973 | 3837 | 3150 | 3474 | 2045
Planned order releases |  | 3150 | 3474 | 2045
Item RM03 | LLC: 1 | Common plastic
| LT: 3 wk | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11
Gross requirements |  | 15332 | 22998 | 22998 | 22998 | 19165
Scheduled receipts
Projected on hand | 42524 | 27192 | 4194 | -18804 | -41802 | -60967
Net requirements |  |  |  | 18804 | 4194 | 14971
Planned order receipts |  |  |  | 18804 | 4194 | 14971
Planned order releases |  | 4194 | 14971
Item RM04 | LLC: 1 | PCBA
| LT: 20 wk | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11
Gross requirements |  | 0 | 11020 | 14000 | 30000 | 25000
Scheduled receipts
Projected on hand | 0 | 0 | -11020 | -25020 | -55020 | -80020
Net requirements |  |  | 11020 | 2980 | 27020
Planned order receipts |  |  | 11020 | 2980 | 27020
Planned order releases
*** RM04 ON HOLD - See PCBA_Recovery_Plan ***
Item RM05 | LLC: 1 | Charger
| LT: 10 wk | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11
Gross requirements |  | 0 | 5510 | 7000 | 15000 | 12500
Scheduled receipts
Projected on hand | 90000 | 90000 | 84490 | 77490 | 62490 | 49990
Net requirements
Planned order receipts
Planned order releases
Item RM06 | LLC: 1 | Fabric
| LT: 5 wk | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11
Gross requirements |  | 25000 | 23725 | 20000 | 0 | 0
Scheduled receipts
Projected on hand | 76000 | 51000 | 27275 | 7275 | 7275 | 7275
Net requirements
Planned order receipts
Planned order releases
Item RM07 | LLC: 1 | Industrial color
| LT: 6 wk | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11
Gross requirements |  | 15000 | 14235 | 12000 | 0 | 0
Scheduled receipts
Projected on hand | 50000 | 35000 | 20765 | 8765 | 8765 | 8765
Net requirements
Planned order receipts
Planned order releases
Item RM08 | LLC: 1 | Special Resin
| LT: 9 wk | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11
Gross requirements |  | 9996 | 14994 | 14994 | 14994 | 12495
Scheduled receipts |  | 38000
Projected on hand | 123000 | 151004 | 136010 | 121016 | 106022 | 93527
Net requirements
Planned order receipts
Planned order releases
Item RM09 | LLC: 1 | Wooden
| LT: 4 wk | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11
Gross requirements |  | 1666 | 2499 | 2499 | 2499 | 2082
Scheduled receipts
Projected on hand | 6500 | 4834 | 2335 | -164 | -2663 | -4745
Net requirements |  |  |  | 164 | 2335
Planned order receipts |  |  |  | 164 | 2335
Planned order releases
Item RM10 | LLC: 1 | Battery
| LT: 11 wk | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11
Gross requirements |  | 0 | 0 | 0 | 0 | 0
Scheduled receipts |  | 5000
Projected on hand | 60000 | 65000 | 65000 | 65000 | 65000 | 65000
Net requirements
Planned order receipts
Planned order releases
Item RM11 | LLC: 1 | Glue
| LT: 3 wk | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11
Gross requirements |  | 0 | 0 | 0 | 0 | 0
Scheduled receipts
Projected on hand | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
Net requirements
Planned order receipts
Planned order releases
Item RM12 | LLC: 1 | Steel metal
| LT: 8 wk | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11
Gross requirements |  | 0 | 1500 | 2910 | 0 | 0
Scheduled receipts
Projected on hand | 5500 | 5500 | 4000 | 1090 | 1090 | 1090
Net requirements
Planned order receipts
Planned order releases
Item RM13 | LLC: 1 | Wheel
| LT: 5 wk | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11
Gross requirements |  | 0 | 2000 | 3880 | 0 | 0
Scheduled receipts |  | 1000
Projected on hand | 6000 | 7000 | 5000 | 1120 | 1120 | 1120
Net requirements
Planned order receipts
Planned order releases
Item RM14 | LLC: 1 | Solar pannel
| LT: 9 wk | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11
Gross requirements |  | 10000 | 12500 | 10150 | 15000 | 12500
Scheduled receipts
Projected on hand | 130000 | 120000 | 107500 | 97350 | 82350 | 69850
Net requirements
Planned order receipts
Planned order releases
Item RM15 | LLC: 1 | Cell
| LT: 7 wk | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11
Gross requirements |  | 4000 | 5000 | 4060 | 6000 | 5000
Scheduled receipts |  | 21000
Projected on hand | 20000 | 37000 | 32000 | 27940 | 21940 | 16940
Net requirements
Planned order receipts
Planned order releases