## Production Plan_new scenario
Production Planning | [8 empty] | Calendar Buckets & Available Capacity (6 workdays/week, Sunday off) | [7 empty] | PCBA Supply Scenario (Robotic A) |  |  | PCBA logistics cost & inventory check (SKU A) | [8 empty] | Scenario KPI Summary
[9 empty] | Bucket | Start | End | Workdays | Workdays/6 | Notes |  |  | Affected SKU | A |  | Air units |  | Air cost/pc | [6 empty] | Total shortage
Start date | 2026-04-15 | [7 empty] | B1 |  |  |  | 0.67 | Mon–Sat; Sunday off |  |  | PCBA per FG (pcs) | 1 |  | Sea units |  | Sea cost/pc | [6 empty] | Total late qty
End date | 2026-05-15 | [7 empty] | B2 |  |  |  | 1 | Mon–Sat; Sunday off |  |  | On-hand GOOD PCBA in VN (pcs) | 0 |  | Total cost | [8 empty] | Total air units
Workdays / week | 6 | [7 empty] | B3 |  |  |  | 1 | Mon–Sat; Sunday off |  |  | Vendor held DEFECT PCBA (pcs) | 30000 |  | Date | Production (A) | Air arr | Sea arr | Reflash arr | Beg Inv | End Inv | Flag |  | Total sea units
Shifts / day | 2 | [7 empty] | B4 |  |  |  | 1 | Mon–Sat; Sunday off |  |  | Reflash equipment available date |  |  | 2026-04-15 | 0 | 0 | 0 | 0 | 0 | 0 | OK |  | Estimated number of air shipments
Lead time min (days) | 7 | [7 empty] | B5 |  |  |  | 0.83 | Mon–Sat; Sunday off |  |  | Reflash capacity (pcs/day) | 4000 |  | 2026-04-16 | 0 | 0 | 0 | 0 | 0 | 0 | OK |  | Estimated number of sea shipments
Lead time max (days) | 14 | [15 empty] | Supplier new PCBA capacity (pcs/day) | 4000 |  | 2026-04-17 | 0 | 0 | 0 | 0 | 0 | 0 | OK |  | Total logistics cost (USD
Note | Factory runs 2 shifts/day, 6 days/week (Sunday off). Plan buckets follow Mon–Sat weeks. | [15 empty] | Air lead time (days) | 3 |  | 2026-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | OK
Overall | [16 empty] | Sea lead time (days) | 21 |  | 2026-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | OK |  | Shipment assumptions
Total workdays in horizon | [16 empty] | Air freight cost (USD/pc) | 2 |  | 2026-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | OK |  | Air shipment capacity per trip (PCBA units) | 1904-08-26
Theoretical shipment request estimated by lead time | [16 empty] | Sea freight cost (USD/pc) | 0 |  | 2026-04-22 | 0 | 0 | 0 | 0 | 0 | 0 | OK |  | Sea shipment capacity per trip (PCBA units) | 1927-05-18
[20 empty] | 2026-04-23 | 0 | 0 | 0 | 0 | 0 | 0 | OK
Demand Aggregated for Production Horizon (15.4-15.5) | [15 empty] | NOTE |  |  |  | 2026-04-24 | 0 | 0 | 0 | 0 | 0 | 0 | OK
[16 empty] | Air cost/pc | Air cost per piece | Chi phí vận chuyển hàng không trên mỗi đơn vị PCBA. |  | 2026-04-25 | 684 | 684 | 0 | 0 | 0 | 0 | OK
SKU | Description | Market | Product group | Fixture | Weekly capacity | Ship request | Demand quantity | Earliest production date (Ship-LeadMax) | Latest production date (Ship-LeadMin) | [6 empty] | Sea cost/pc | Sea cost per piece | Chi phí vận chuyển đường biển trên mỗi đơn vị PCBA. |  | 2026-04-27 | 0 | 0 | 0 | 0 | 0 | 0 | OK
A | 2026 Automatic Robot ver | US | Electronic Toy | 123AB | 15000 | 2026-05-08 | [9 empty] | Total cost | Total logistics cost | Tổng chi phí logistics phát sinh từ phương án air/sea cho PCBA. |  | 2026-04-28 | 0 | 0 | 0 | 0 | 0 | 0 | OK
A | 2026 Automatic Robot ver | US | Electronic Toy | 123AB | 15000 | 2026-05-15 | [9 empty] | Prod(A) | Production quantity of SKU A | Số lượng SKU A được sản xuất trong ngày; cũng là lượng PCBA bị tiêu hao trong ngày nếu 1 sản phẩm dùng 1 PCBA. |  | 2026-04-29 | 0 | 0 | 0 | 0 | 0 | 0 | OK
A | 2026 Automatic Robot ver | US | Electronic Toy | 123AB | 15000 | 2026-05-22 | [9 empty] | Air arr | Air arrival | Số lượng PCBA thực nhận trong ngày từ phương án vận chuyển air. |  | 2026-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | OK
A | 2026 Automatic Robot ver | US | Electronic Toy | 123AB | 15000 | 2026-05-29 | [9 empty] | Sea arr | Sea arrival | Số lượng PCBA thực nhận trong ngày từ phương án vận chuyển sea. |  | 2026-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | OK
B | 2025 Barbie ver colorful | US | Doll | 123AB | 15000 | 2026-05-15 | [9 empty] | Reflash arr | Reflash arrival / recovered usable PCBA arrival | Số lượng PCBA bổ sung trong ngày từ nguồn reflash/rework/phục hồi nội bộ. |  | 2026-05-02 | 2500 | 2500 | 0 | 0 | 0 | 0 | OK
B | 2025 Barbie ver colorful | US | Doll | 123AB | 15000 | 2026-05-22 | [9 empty] | Beg Inv | Beginning Inventory | Tồn kho đầu ngày của PCBA. |  | 2026-05-04 | 1998 | 1998 | 0 | 0 | 0 | 0 | OK
B | 2025 Barbie ver colorful | US | Doll | 123AB | 15000 | 2026-05-29 | [9 empty] | End Inv | Ending Inventory | Tồn kho cuối ngày của PCBA sau khi cộng arrival và trừ lượng dùng cho sản xuất. |  | 2026-05-05 | 0 | 0 | 0 | 0 | 0 | 0 | OK
C | 2026 Castle & Farm Blocks | UK | Building & Construction Toy | 456CD | 5000 | 2026-05-15 | [9 empty] | Inv | Inventory | Tồn kho. |  | 2026-05-06 | 2500 | 0 | 0 | 4000 | 0 | 1500 | OK
C | 2026 Castle & Farm Blocks | UK | Building & Construction Toy | 456CD | 5000 | 2026-05-22 | [9 empty] | Flag | Status flag | Cờ cảnh báo tình trạng tồn kho trong ngày. |  | 2026-05-07 | 2500 | 0 | 0 | 4000 | 1500 | 3000 | OK
C | 2026 Castle & Farm Blocks | UK | Building & Construction Toy | 456CD | 5000 | 2026-05-29 | [9 empty] | OK | OK / Inventory feasible | Tồn kho không âm, ngày đó khả thi về mặt vật tư. |  | 2026-05-08 | 2500 | 0 | 0 | 4000 | 3000 | 4500 | OK
D | 2026 Animal Animation Book | UK | Educational Toy | 456CD | 5000 | 2026-05-15 | [9 empty] | NEG_INV | Negative Inventory | Tồn kho âm, nghĩa là kế hoạch sản xuất ngày đó không khả thi nếu không có thêm PCBA. |  | 2026-05-09 | 2500 | 0 | 0 | 4000 | 4500 | 6000 | OK
D | 2026 Animal Animation Book | UK | Educational Toy | 456CD | 5000 | 2026-05-22 | [9 empty] | units | Units / quantity | Số đơn vị, số lượng. |  | 2026-05-11 | 2500 | 0 | 0 | 4000 | 6000 | 7500 | OK
D | 2026 Animal Animation Book | UK | Educational Toy | 456CD | 5000 | 2026-05-29 | [9 empty] | pc | piece | Một đơn vị/cái. |  | 2026-05-12 | 2500 | 0 | 0 | 4000 | 7500 | 9000 | OK
E | 2026 Scooter ver | Australia | Outdoor & Sports Toy | 789EF | 3000 | 2026-05-08 | [13 empty] | 2026-05-13 | 2500 | 0 | 0 | 4000 | 9000 | 10500 | OK
E | 2026 Scooter ver | Australia | Outdoor & Sports Toy | 789EF | 3000 | 2026-05-15 | [13 empty] | 2026-05-14 | 2500 | 0 | 0 | 2000 | 10500 | 10000 | OK
E | 2026 Scooter ver | Australia | Outdoor & Sports Toy | 789EF | 3000 | 2026-05-22 | [13 empty] | 2026-05-15 | 2500 | 0 | 0 | 0 | 10000 | 7500 | OK
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 3000 | 2026-05-01
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 3000 | 2026-05-08
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 3000 | 2026-05-15
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 3000 | 2026-05-22
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 3000 | 2026-05-29
Production Plan (Daily workday view)
SKU | Description | Market | Product group | Fixture | Weekly cap | Ship request | Demand quantity | Earliest production date | Latest production date | Week 1 |  |  |  | Week 2 | [5 empty] | Week 3 | [5 empty] | Week 4 | [5 empty] | Week 5 |  |  |  |  | Planned total | Shortage | Risk | Late quantity | Horizon status
[10 empty] | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 3000 | 2026-05-01 | 588 |  |  | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A | 2026 Automatic Robot ver | US | Electronic Toy | 123AB | 15000 | 2026-05-08 | 684 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E | 2026 Scooter ver | Australia | Outdoor & Sports Toy | 789EF | 3000 | 2026-05-08 | 472 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 3000 | 2026-05-08 | 4028 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 500 | 28 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A | 2026 Automatic Robot ver | US | Electronic Toy | 123AB | 15000 | 2026-05-15 | 20000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 1998 | 0 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0
B | 2025 Barbie ver colorful | US | Doll | 123AB | 15000 | 2026-05-15 | 5502 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 502 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | 2026 Castle & Farm Blocks | UK | Building & Construction Toy | 456CD | 5000 | 2026-05-15 | 4320 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833 | 0 | 833 | 833 | 833 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D | 2026 Animal Animation Book | UK | Educational Toy | 456CD | 5000 | 2026-05-15 | 2430 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833 | 0 | 833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E | 2026 Scooter ver | Australia | Outdoor & Sports Toy | 789EF | 3000 | 2026-05-15 | 300 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 3000 | 2026-05-15 | 4200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 200 | 500 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0
A | 2026 Automatic Robot ver | US | Electronic Toy | 123AB | 15000 | 2026-05-22 | 20000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500
B | 2025 Barbie ver colorful | US | Doll | 123AB | 15000 | 2026-05-22 | 15658 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | 2026 Castle & Farm Blocks | UK | Building & Construction Toy | 456CD | 5000 | 2026-05-22 | 8370 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833 | 833 | 833 | 0 | 0 | 833 | 0
D | 2026 Animal Animation Book | UK | Educational Toy | 456CD | 5000 | 2026-05-22 | 9990 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833 | 833 | 0 | 0
E | 2026 Scooter ver | Australia | Outdoor & Sports Toy | 789EF | 3000 | 2026-05-22 | 698 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 198 | 0 | 0 | 0
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 3000 | 2026-05-22 | 3802 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 302 | 500 | 500 | 500
A | 2026 Automatic Robot ver | US | Electronic Toy | 123AB | 15000 | 2026-05-29 | 11000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B | 2025 Barbie ver colorful | US | Doll | 123AB | 15000 | 2026-05-29 | 8865 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | 2026 Castle & Farm Blocks | UK | Building & Construction Toy | 456CD | 5000 | 2026-05-29 | 11782 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D | 2026 Animal Animation Book | UK | Educational Toy | 456CD | 5000 | 2026-05-29 | 5840 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 833
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 3000 | 2026-05-29 | 4500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scenario KPI Summary
Total shortage
Total late qty
Total air units
Total sea units
Estimated number of air shipments
Estimated number of sea shipments
Total logistics cost (USD)
Shipment assumptions
[20 empty] | Air shipment capacity per trip (PCBA units) | 1700
[20 empty] | Sea shipment capacity per trip (PCBA units) | 10000