## Scenario_Result
SKU | Description | Market | Product Group | Fixture | Priority | Weekly Cap | Ship Request | Demand Qty | 15/04 | 16/04 | 17/04 | 18/04 | 20/04 | 21/04 | 22/04 | 23/04 | 24/04 | 25/04 | 27/04 | 28/04 | 29/04 | 30/04 | 01/05 | 02/05 | 04/05 | 05/05 | 06/05 | 07/05 | 08/05 | 09/05 | 11/05 | 12/05 | 13/05 | 14/05 | 15/05 | Beg Inv | Period Prod | Available | End Inv | Shortage | Risk | Horizon Status
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 2 | 3000 | 2026-05-01 | 588 | 500 | 500 | 500 | 500 | 500 | 500 | 0 | 500 | 500 | 500 | 500 | 500 | 30 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6030 | 6030 | 5442 | 0 | OK | WITHIN_HORIZON
A | 2026 Automatic Robot ver | US | Electronic Toy | 123AB | 1 | 15000 | 2026-05-08 | 684 | 0 | 0 | 0 | 0 | 510 | 0 | 2500 | 0 | 0 | 2500 | 2500 | 0 | 0 | 0 | 2500 | 2000 | 2500 | 2500 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25010 | 25010 | 24326 | 0 | OK | WITHIN_HORIZON
E | 2026 Scooter ver | Australia | Outdoor & Sports Toy | 789EF | 1 | 3000 | 2026-05-08 | 472 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 470 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1470 | 1470 | 998 | 0 | OK | WITHIN_HORIZON
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 2 | 3000 | 2026-05-08 | 4028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 500 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 5442 | 3000 | 8442 | 4414 | 0 | OK | WITHIN_HORIZON
A | 2026 Automatic Robot ver | US | Electronic Toy | 123AB | 1 | 15000 | 2026-05-15 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 24326 | 15000 | 39326 | 19326 | 0 | OK | WITHIN_HORIZON
B | 2025 Barbie ver colorful | US | Doll | 123AB | 2 | 15000 | 2026-05-15 | 5502 | 2500 | 2500 | 2500 | 2500 | 1990 | 2500 | 0 | 2500 | 2500 | 0 | 0 | 2500 | 2500 | 2500 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27490 | 27490 | 21988 | 0 | OK | WITHIN_HORIZON
C | 2026 Castle & Farm Blocks | UK | Building & Construction Toy | 456CD | 1 | 5000 | 2026-05-15 | 4320 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 0 | 22491 | 22491 | 18171 | 0 | OK | WITHIN_HORIZON
D | 2026 Animal Animation Book | UK | Educational Toy | 456CD | 2 | 5000 | 2026-05-15 | 2430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2430 | SHORTAGE | WITHIN_HORIZON
E | 2026 Scooter ver | Australia | Outdoor & Sports Toy | 789EF | 1 | 3000 | 2026-05-15 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 998 | 0 | 998 | 698 | 0 | OK | WITHIN_HORIZON
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 2 | 3000 | 2026-05-15 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 500 | 500 | 500 | 500 | 4414 | 3000 | 7414 | 3214 | 0 | OK | WITHIN_HORIZON
A | 2026 Automatic Robot ver | US | Electronic Toy | 123AB | 1 | 15000 | 2026-05-22 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19326 | 0 | 19326 | 0 | 674 | SHORTAGE | BEYOND_HORIZON
B | 2025 Barbie ver colorful | US | Doll | 123AB | 2 | 15000 | 2026-05-22 | 15658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21988 | 0 | 21988 | 6330 | 0 | OK | BEYOND_HORIZON
C | 2026 Castle & Farm Blocks | UK | Building & Construction Toy | 456CD | 1 | 5000 | 2026-05-22 | 8370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18171 | 0 | 18171 | 9801 | 0 | OK | BEYOND_HORIZON
D | 2026 Animal Animation Book | UK | Educational Toy | 456CD | 2 | 5000 | 2026-05-22 | 9990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9990 | SHORTAGE | BEYOND_HORIZON
E | 2026 Scooter ver | Australia | Outdoor & Sports Toy | 789EF | 1 | 3000 | 2026-05-22 | 698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 698 | 0 | 698 | 0 | 0 | OK | BEYOND_HORIZON
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 2 | 3000 | 2026-05-22 | 3802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3214 | 0 | 3214 | 0 | 588 | SHORTAGE | BEYOND_HORIZON
A | 2026 Automatic Robot ver | US | Electronic Toy | 123AB | 1 | 15000 | 2026-05-29 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 | SHORTAGE | BEYOND_HORIZON
B | 2025 Barbie ver colorful | US | Doll | 123AB | 2 | 15000 | 2026-05-29 | 8865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6330 | 0 | 6330 | 0 | 2535 | SHORTAGE | BEYOND_HORIZON
C | 2026 Castle & Farm Blocks | UK | Building & Construction Toy | 456CD | 1 | 5000 | 2026-05-29 | 11782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9801 | 0 | 9801 | 0 | 1981 | SHORTAGE | BEYOND_HORIZON
D | 2026 Animal Animation Book | UK | Educational Toy | 456CD | 2 | 5000 | 2026-05-29 | 5840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5840 | SHORTAGE | BEYOND_HORIZON
F | 2025 Fantasy Spaceship Model DIY kits | US | Arts & Crafts Toy | 789EF | 2 | 3000 | 2026-05-29 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | SHORTAGE | BEYOND_HORIZON

## PCBA_Supply_Timeline
Workday | Date | Cal Day | Air Arrived | Sea Arrived | Reflash Avail | Cumul PCBA | A Prod Today | Cumul A Prod | PCBA Used (cum) | PCBA Remaining
1 | 2026-04-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 2026-04-16 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 2026-04-17 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 2026-04-18 | 3 | 4000 | 0 | 0 | 4000 | 0 | 0 | 0 | 4000
5 | 2026-04-20 | 5 | 0 | 0 | 0 | 4000 | 510 | 510 | 1020 | 2980
6 | 2026-04-21 | 6 | 0 | 0 | 0 | 4000 | 0 | 510 | 1020 | 2980
7 | 2026-04-22 | 7 | 2020 | 0 | 0 | 6020 | 2500 | 3010 | 6020 | 0
8 | 2026-04-23 | 8 | 4000 | 0 | 0 | 10020 | 0 | 3010 | 6020 | 4000
9 | 2026-04-24 | 9 | 0 | 0 | 0 | 10020 | 0 | 3010 | 6020 | 4000
10 | 2026-04-25 | 10 | 4000 | 0 | 0 | 14020 | 2500 | 5510 | 11020 | 3000
11 | 2026-04-27 | 12 | 3000 | 0 | 0 | 17020 | 2500 | 8010 | 16020 | 1000
12 | 2026-04-28 | 13 | 0 | 0 | 0 | 17020 | 0 | 8010 | 16020 | 1000
13 | 2026-04-29 | 14 | 0 | 0 | 0 | 17020 | 0 | 8010 | 16020 | 1000
14 | 2026-04-30 | 15 | 0 | 0 | 0 | 17020 | 0 | 8010 | 16020 | 1000
15 | 2026-05-01 | 16 | 4000 | 0 | 0 | 21020 | 2500 | 10510 | 21020 | 0
16 | 2026-05-02 | 17 | 4000 | 0 | 0 | 25020 | 2000 | 12510 | 25020 | 0
17 | 2026-05-04 | 19 | 4000 | 0 | 0 | 31020 | 2500 | 15010 | 30020 | 1000
18 | 2026-05-05 | 20 | 4000 | 0 | 0 | 35020 | 2500 | 17510 | 35020 | 0
19 | 2026-05-06 | 21 | 0 | 0 | 370000 | 405020 | 2500 | 20010 | 40020 | 365000
20 | 2026-05-07 | 22 | 0 | 0 | 370000 | 405020 | 2500 | 22510 | 45020 | 360000
21 | 2026-05-08 | 23 | 0 | 0 | 370000 | 405020 | 2500 | 25010 | 50020 | 355000
22 | 2026-05-09 | 24 | 0 | 0 | 370000 | 405020 | 2500 | 27510 | 55020 | 350000
23 | 2026-05-11 | 26 | 0 | 0 | 370000 | 405020 | 2500 | 30010 | 60020 | 345000
24 | 2026-05-12 | 27 | 0 | 0 | 370000 | 405020 | 2500 | 32510 | 65020 | 340000
25 | 2026-05-13 | 28 | 0 | 0 | 370000 | 405020 | 2500 | 35010 | 70020 | 335000
26 | 2026-05-14 | 29 | 0 | 0 | 370000 | 405020 | 2500 | 37510 | 75020 | 330000
27 | 2026-05-15 | 30 | 0 | 0 | 370000 | 405020 | 2500 | 40010 | 80020 | 325000

## Cost_Analysis
PCBA Scenario Cost Analysis
Item | Value
PCBA on hold (defective) | 370,000
Reflash available from | Day 21 (2026-05-06)
Supplier daily capacity | 4,000 PCBA/day
Logistics Decision
Total PCBA by AIR | 35,020
Total PCBA by SEA | 0
Air lead time | 3 days
Sea lead time | 21 days
Cost Breakdown
Air freight cost | $70,040.00
= 35,020 PCBA x $2.0/unit
Sea freight extra cost | $0.00
Reflash cost | $0.00 (equipment only)
TOTAL SCENARIO COST | $70,040.00
Production Impact
Total demand | 143,029
Total planned | 103,491
Total shortage | 39,538
SKU A demand | 51,684
SKU A planned | 40,010

## KPI_Summary
Metric | Value
Solver Status | Optimal
Total Demand Lines | 21
Planning Horizon | 27 workdays
Total Demand Qty | 143029
Total Planned Qty | 103491
Total Shortage Qty | 39538
Pri-1 Shortage | 13,655 / 77,626 (17.6%)
Pri-2 Shortage | 25,883 / 65,403 (39.6%)
Air Freight PCBA | 35020
Sea Freight PCBA | 0
Air Freight Cost (USD) | $70,040.00

## Fixture_Load_Detail
Fixture | Daily Cap | 15/04 | 16/04 | 17/04 | 18/04 | 20/04 | 21/04 | 22/04 | 23/04 | 24/04 | 25/04 | 27/04 | 28/04 | 29/04 | 30/04 | 01/05 | 02/05 | 04/05 | 05/05 | 06/05 | 07/05 | 08/05 | 09/05 | 11/05 | 12/05 | 13/05 | 14/05 | 15/05
123AB | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500
456CD | 833.3 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833 | 833
789EF | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500

## SKU_Inventory_Flow
SKU | Priority | Period | Ship Date | Beg Inv | Period Prod | Available | Demand | End Inv | Shortage | Risk
A | 1 | 1 | 2026-05-08 | 0 | 25010 | 25010 | 684 | 24326 | 0 | OK
A | 1 | 2 | 2026-05-15 | 24326 | 15000 | 39326 | 20000 | 19326 | 0 | OK
A | 1 | 3 | 2026-05-22 | 19326 | 0 | 19326 | 20000 | 0 | 674 | SHORTAGE
A | 1 | 4 | 2026-05-29 | 0 | 0 | 0 | 11000 | 0 | 11000 | SHORTAGE
B | 2 | 1 | 2026-05-15 | 0 | 27490 | 27490 | 5502 | 21988 | 0 | OK
B | 2 | 2 | 2026-05-22 | 21988 | 0 | 21988 | 15658 | 6330 | 0 | OK
B | 2 | 3 | 2026-05-29 | 6330 | 0 | 6330 | 8865 | 0 | 2535 | SHORTAGE
C | 1 | 1 | 2026-05-15 | 0 | 22491 | 22491 | 4320 | 18171 | 0 | OK
C | 1 | 2 | 2026-05-22 | 18171 | 0 | 18171 | 8370 | 9801 | 0 | OK
C | 1 | 3 | 2026-05-29 | 9801 | 0 | 9801 | 11782 | 0 | 1981 | SHORTAGE
D | 2 | 1 | 2026-05-15 | 0 | 0 | 0 | 2430 | 0 | 2430 | SHORTAGE
D | 2 | 2 | 2026-05-22 | 0 | 0 | 0 | 9990 | 0 | 9990 | SHORTAGE
D | 2 | 3 | 2026-05-29 | 0 | 0 | 0 | 5840 | 0 | 5840 | SHORTAGE
E | 1 | 1 | 2026-05-08 | 0 | 1470 | 1470 | 472 | 998 | 0 | OK
E | 1 | 2 | 2026-05-15 | 998 | 0 | 998 | 300 | 698 | 0 | OK
E | 1 | 3 | 2026-05-22 | 698 | 0 | 698 | 698 | 0 | 0 | OK
F | 2 | 1 | 2026-05-01 | 0 | 6030 | 6030 | 588 | 5442 | 0 | OK
F | 2 | 2 | 2026-05-08 | 5442 | 3000 | 8442 | 4028 | 4414 | 0 | OK
F | 2 | 3 | 2026-05-15 | 4414 | 3000 | 7414 | 4200 | 3214 | 0 | OK
F | 2 | 4 | 2026-05-22 | 3214 | 0 | 3214 | 3802 | 0 | 588 | SHORTAGE
F | 2 | 5 | 2026-05-29 | 0 | 0 | 0 | 4500 | 0 | 4500 | SHORTAGE